## Project Planner
Smart_Box Project Plan
[9 empty] | Plan Duration | [5 empty] | Actual Start
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | % Complete |  |  |  |  | Actual (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (WEEK)
[6 empty] | January |  |  |  |  | Febuary |  |  |  | March
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Collect Data: | 5 | 1 | 5 | 1 | 100%
Project planing | 5 | 1 | 5 | 1 | 100%
Project Flowchart Overview | 5 | 1 | 5 | 1 | 100%
Data preprocessing | 5 | 1 | 5 | 1 | 100%
Data annotation | 5 | 1 | 5 | 1 | 100%
Reviewing design 3-Feb-2024 | 5 | 1 | 6 | 1 | 100%
Model Develop: | 6 | 2 | 6 | 1 | 100%
Model Architecture Design | 6 | 1 | 6 | 1 | 100%
Model Components | 6 | 1 | 6 | 1 | 100%
Model Input | 6 | 1 | 6 | 1 | 100%
Model Config and Train | 6 | 2 | 6 | 2 | 100%
Reviewing design based on Meeting | 6 | 2 | 6 | 2 | 100%
Model Evaluation: | 7 | 1 | 6 | 2 | 100%
Model Test | 7 | 1 | 7 | 1 | 100%
Performances | 7 | 1 | 7 | 1 | 100%
Reviewing design based on Meeting | 7 | 1 | 7 | 1 | 100%
Deploy: | 8 | 1 | 8 | 1 | 100%
Deployment Design by Flask-python | 8 | 1 | 8 | 1 | 100%
Flask File Components | 8 | 1 | 8 | 1 | 100%
Authentication & Checking Standard | 8 | 1 | 8 | 1 | 100%
Fixing issues that arise during testing | 8 | 1 | 8 | 1 | 100%
Reviewing design based on Meeting | 8 | 1 | 8 | 1 | 100%
Presentation: | 9 | 1 | 8 | 1 | 100%
Presentation Preparation | 9 | 1 | 8 | 1 | 100%
Reviewing design based on Meeting | 9 | 1 | 8 | 1 | 100%